ElderOS Vision ML Model — 1-Week POC Sprint Plan Target: Stable Demo · Bed-Exit · On-Floor · Fall-Suspected

# Executive Summary

This plan delivers a stable ElderOS ML demo within 1 week using a rules-first approach on the Jetson Orin edge platform. By relying on pre-trained pose estimation and rule-based event logic — rather than training a custom ML model from scratch — the team can produce reliable, demo-ready detection of all three target outcomes: Bed-Exit, On-Floor, and Fall-Suspected.

Recommended Strategy: Rules-First → ML-Ready Use rule-based pose detection for the 1-week POC demo. This delivers reliable Bed-Exit, On-Floor, and Fall-Suspected alerts without any ML training time. Simultaneously capture labeled event data to train a TCN classifier for production hardening post-POC.

# Target Demo Outcomes

All three events must fire reliably during the POC demo with low false positives.

| 🛏 Bed-Exit | 🏥 On-Floor | ⚠️ Fall-Suspected |
| --- | --- | --- |
| Pelvis/torso keypoints leave bed-zone + upright posture for N frames | Torso height low + lying angle sustained ≥ N seconds | Rapid hip height drop + transition to On-Floor state |
| Precision target: >90% | Precision target: >90% | False positives: <1/room/night |

# 1-Week Sprint Schedule

Each day has a clear deliverable. Scope is intentionally narrow — every day must produce something that runs.

| Day | Theme | Tasks & Deliverables |
| --- | --- | --- |
| Day 1 MONDAY | Constraints + Hardware Lock | • Confirm Jetson Orin NX (8GB+) is available • Set RTSP stream from 1 camera (PoE, 1080p, 2.8mm) • Define 3 privacy defaults: no audio, no continuous recording, edge-only • Sketch bed-zone calibration for the test room • OUTPUT: 1-page Privacy & Data Handling spec |
| Day 2 TUESDAY | DeepStream Pipeline Running | • Install DeepStream container on Orin • Verify RTSP → Person detection → Pose estimation chain • Confirm 17-keypoint output per frame at ≥8 FPS • Apply EMA/Kalman smoothing to keypoints • OUTPUT: Live keypoint stream visible on test dashboard |
| Day 3 WEDNESDAY | Rules Baseline: Bed-Exit + On-Floor | • Implement bed-zone polygon (configurable per room) • Code Bed-Exit rule: pelvis/torso leaves zone + N upright frames • Code On-Floor rule: hip height threshold + lying angle + duration • Run against recorded test footage to tune thresholds • OUTPUT: Bed-Exit and On-Floor firing on test clips |
| Day 4 THURSDAY | Fall-Suspected + Alert Pipeline | • Code Fall-Suspected rule: hip height drop velocity + On-Floor transition • Wire Jetson → ElderOS API (MQTT or HTTP) • Implement SMS/Push notification on event • Test alert latency end-to-end (target: <5 seconds) • OUTPUT: All 3 events alerting end-to-end |
| Day 5 FRIDAY | Demo Hardening + Calibration | • Run 20+ simulated test scenarios (bed exit, kneel, floor, fall) • Tune confidence thresholds to minimize false positives • Add occlusion handling flag (staff present) • Build simple POC dashboard: room grid + live event log • OUTPUT: Demo-ready system with <1 false alarm per test session |
| Days 6-7 WEEKEND | Buffer + Final Polish | • Fix any edge cases found during Friday testing • Add blurred preview mode for privacy demo • Prepare POC KPI summary (precision, latency, false positives) • Dry-run the full demo scenario 3+ times • OUTPUT: Rehearsed, stable demo ready to show investors/buyers |

# Recommended Technology Stack

Use pretrained models for pose estimation. Only build what is proprietary to ElderOS.

| Layer | Technology | Notes |
| --- | --- | --- |
| Hardware | NVIDIA Jetson Orin NX (8GB+) | Provides headroom for 8–12 rooms at 8–10 FPS |
| Camera | PoE 1080p, 2.8mm, IR (Hikvision / Dahua) | Ceiling/corner mount; ONVIF/RTSP standard |
| Ingestion | GStreamer + NVIDIA DeepStream | 3–8 FPS capture; RTSP stream per room |
| Pose Model | NVIDIA TAO BodyPoseNet or TRT-Pose | Pretrained — do NOT train from scratch for POC |
| Keypoint Smoothing | EMA / Kalman Filter | Reduces jitter before rule evaluation |
| Event Logic | Rules Engine (Python) | Bed-Exit, On-Floor, Fall-Suspected rules |
| Alert Transport | MQTT or HTTP → ElderOS API | Target latency <5 seconds end-to-end |
| ML (Post-POC) | TCN on 16–32 frame pose windows | Train after 500–2000 labeled events are captured |
| Runtime Optimization | ONNX → TensorRT (FP16) | For production hardening after POC |

# POC Success Criteria (KPIs)

Set and agree on these thresholds before the demo. They anchor all tuning decisions.

| Metric | POC Target | How to Measure |
| --- | --- | --- |
| Bed-Exit detection precision | >90% | Run 10+ staged bed-exit scenarios, count correct detections |
| On-Floor detection precision | >90% | Staged floor scenarios — lying, kneeling, sitting low |
| Fall-Suspected false positives | <1 per room per night | Monitor overnight with no real residents; count false alerts |
| Alert end-to-end latency | <5 seconds | Measure Jetson event time → notification received |
| System uptime during demo | 100% | No crashes, no missed stream reconnects |

# Build vs. Use Pretrained

The ML model is not your moat. The pipeline, calibration, event logic, and alert workflow are.

| ✅ Build (Your Moat) | 📦 Use Pretrained / Open Source |
| --- | --- |
| - Keypoints event store + schema - Bed-zone calibration logic - Rules engine (Bed-Exit, On-Floor, Fall-Suspected) - Alert workflow (ElderOS API, MQTT, push) - Event capture + labeling UI - TCN temporal classifier (post-POC) - Audit logs + RBAC | - Pose model: TAO BodyPoseNet or TRT-Pose - Person detection: YOLOv8-nano (TensorRT) - DeepStream pipeline (NVIDIA official) - EMA/Kalman (standard DSP library) |

# Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Night-vision IR washout near bed | High | Test specific camera model in real room at night on Day 1; budget for camera swap if needed |
| Pose estimation fails on occluded/side views | High | Add occlusion confidence flag; rule only fires if pose_conf >0.5 for N frames |
| False positives from staff care activities | High | Tag 'staff_present' via room-level override; use event capture to label hard negatives |
| Bed-zone calibration inaccurate | Medium | Implement calibration UI on Day 2; validate with 5 manual bed-exit walkthroughs |
| DeepStream version/driver conflicts on Orin | Medium | Use the NVIDIA-official DeepStream Docker image; pre-test on Day 1 |
| Alert latency >5s | Low | Pre-optimize MQTT pipeline; test end-to-end on Day 3 |

# Post-POC ML Roadmap

The rules-based POC creates the data foundation for training the production TCN model. Start capturing labeled events from Day 3 onwards.

| Phase | What to Do After the POC Demo |
| --- | --- |
| Week 2–4 | Event capture during real/staged resident activity. Start labeling: normal, bed_exit, on_floor, fall. Target 500–2000 labeled windows. |
| Week 3–5 | Train TCN classifier on labeled pose sequences (16–32 frames at 8–16 FPS). Use weighted cross-entropy + focal loss. Evaluate: confusion matrix + false positives per night. |
| Week 5–8 | Convert ONNX → TensorRT (FP16). Deploy on Jetson. Set hybrid rule: fire fall alert only if p_fall > 0.7 AND on-floor persists 3–5s. Add day/night profiles. |
| Phase 1B | Expand to multi-room deployment. Add mmWave radar fusion for hybrid rooms (>95% accuracy). Remote model update via Docker pull. Per-facility threshold tuning. |

# Immediate Next Steps (Do This First)

- Confirm Jetson Orin NX (8GB+) hardware is available and running Ubuntu LTS + Docker

- Pick pose model: NVIDIA TAO BodyPoseNet or TRT-Pose (both run natively on Orin)

- Set up 1 test camera with RTSP stream and verify DeepStream can ingest it

- Draw the bed-zone polygon for the test room (this is the most critical calibration step)

- Implement baseline rules + alert push — this IS the POC demo core

- Start event-only capture on Day 3 to begin building the ML training dataset

ElderOS Vision · Phase 1 ML POC · Confidential · Document v1.0