Recommended build plan (Resident rooms + Jetson Orin, privacy-first)

Architecture choice (my recommendation)

Pose-first pipeline (skeleton keypoints) + temporal classifier (TCN) + rules safety rails.

Why: fastest to stabilize, easiest privacy story, runs well on Orin, fewer false alarms than “raw video action recognition”.

Phase 0 — Lock constraints (Day 1–2)

Privacy + compliance defaults (non-negotiable)

- Edge-only inference (Jetson Orin)

- No audio

- No continuous recording

- Event-only clips (optional; short, encrypted, auto-expire)

- Face/scene blur on any preview

- RBAC + audit logs

Deliverable: 1-page “POC Privacy & Data Handling” spec.

Phase 1 — Hardware + camera placement (Week 1)

Room camera standard

- PoE turret/dome, 1080p, wide angle (≈2.8mm), IR optional

- Mount: corner ceiling line of sight to bed + floor next to bed

Sizing (rule of thumb)

- Start with 1 Jetson Orin per 8–12 rooms at ~8–10 FPS pose inference.

- For POC: 20–30 rooms → 2–4 Orins depending on FPS and model.

Deliverables:

- Room mounting template + “bed zone” calibration checklist

- Network plan (VLAN, RTSP, PoE switch)

Phase 2 — Edge inference pipeline (Week 1–2)

Goal

Get stable keypoints stream per room and basic events without ML training.

DeepStream pipeline (per camera)

- RTSP ingest

- Person detection (optional gating)

- Pose estimation model

- Keypoint smoothing (EMA / Kalman)

- Feature extraction (per frame + per window)

- Event trigger (rules baseline)

- Output events to ElderOS API (MQTT/HTTP)

Output schema (store this, not video)

Per frame:

- timestamp, room_id

- keypoints[17 or 34] = (x,y,conf)

- bbox, person_id, pose_conf

Deliverables:

- Running DeepStream container on Orin

- “Keypoints-only” event stream to a test dashboard

Phase 3 — Rules baseline (Week 2)

Before training any ML, ship a baseline:

Events to implement first

- Bed exit: pelvis/torso keypoints leave bed-zone + vertical posture for N frames

- On-floor: torso height low + lying angle sustained N seconds

- Fall candidate: rapid hip height drop + transition to on-floor

This baseline also becomes your “safety rails” later.

Deliverable:

- Alerting working end-to-end (Jetson → ElderOS → SMS/Push)

Phase 4 — Data collection + labeling (Week 2–4)

Reality: you won’t get many real falls

So you train on:

- Many “non-fall” transitions (sit, kneel, pick up item, staff care)

- Bed exits

- “On-floor” events (staged by staff in controlled training room if allowed)

Event-only capture (recommended)

When rules trigger, save:

- 10s before + 10s after

- Store locally encrypted, auto-delete after 7–14 days

- If privacy is tight: store only keypoint sequences + 2–3 blurred thumbnails.

Labeling workflow

Label each event:

- normal, bed_exit, on_floor, fall

- optional tags: wheelchair, walker, staff_present, occluded, night

Target dataset for first usable model:

- 500–2000 labeled event windows

- Imbalanced is OK; you’ll use weighted loss.

Deliverables:

- Simple labeling UI (web) + dataset export to training box

Phase 5 — Train the temporal classifier (Week 3–5)

Model recommendation

TCN (Temporal Convolutional Network) on pose features.

Why TCN:

- Low latency

- Stable on edge

- Easier than LSTM/Transformers for deployment

Input features (per frame)

Compute from keypoints:

- Hip height (relative to bbox)

- Torso angle

- Velocity/acceleration of hips/torso

- Distance to bed-zone

- “Lying score” vs “standing score”

- Confidence stats (to detect occlusion)

Window:

- 1–2 seconds (e.g., 16–32 frames at 8–16 FPS)

Outputs

- p_fall, p_bed_exit, p_on_floor, p_normal

Training approach

- Weighted cross entropy / focal loss

- Hard negative mining (false alarms)

- Split by room to avoid leakage

Deliverables:

- model.onnx

- Evaluation report: confusion matrix + false positives/night

Phase 6 — Deploy on Jetson + harden (Week 5–8)

Runtime

- Convert ONNX → TensorRT engine (FP16)

- Integrate into DeepStream via custom plugin or sidecar inference service

- Keep rules as post-processor:

  - Example: trigger fall alert only if p_fall > 0.7 AND “on-floor” persists 3–5s

Operational hardening

- Per-room calibration (bed zone, camera perspective)

- Day/night profiles

- Occlusion handling (staff in room)

- Alert throttling + escalation rules

Deliverables:

- Versioned model rollout

- Remote config + health checks

- POC KPI dashboard

What ElderOS should build vs buy (pragmatic recommendation)

Build now

- The pipeline, keypoints store, event engine, dashboard, alert workflow, audit logs
These are your moat.

Use pretrained

- Pose model (don’t reinvent)

- Only train your temporal classifier + calibrations

Consider commercial only if…

- They demand guaranteed fall detection in <30 days and you can’t collect data fast enough.

POC success criteria (set before install)

- Bed exit detection precision: >90%

- On-floor detection precision: >90%

- Fall alert false positives: <1 per room per night (initial realistic target)

- Median alert latency: <5 seconds

“How to” execution checklist (what you do next week)

- Pick pose model stack (NVIDIA TAO BodyPoseNet or TRT Pose)

- Build DeepStream RTSP→pose→keypoints output for 1 camera

- Add bed-zone calibration UI

- Implement baseline rules + alert push

- Start event-only capture + labeling

- Train TCN on pose sequences

- Deploy TensorRT classifier + rails